EASTERN REGION ROLL-OUT  PLAN OF E-LEARNING: PHASE 1 ( FET)

| TIME-FRAME | VENUE | ACITIVITY | RESOURCES | TARGET GROUP | RESPONSIBILTY | DURATION |
| --- | --- | --- | --- | --- | --- | --- |
| 06-02-09 | REGIONAL OFFICE | REPORTING | LAP TPOS&DESK TOPS, FLASH DISK,DATA PROJECTOR ETC. | ROB’S | EDUCATION CONVENOR | 1 DAY |
| LAST WEEK FEBRUARY | REGIONAL OFFICE | REPORTING | SAME AS ABOVE | REC | ROB’S | 1 DAY |
| 1ST WEEK MARCH | REGIONAL OFFICE | PLANNING SESSION | SOFT & HARD WARE | MASTER TRAINERS | EDUCATION CONVENOR | 1 DAY |
| 2ND WEEK MARCH | TRINSET | TRAINING OF TRAINERS | LAP TPOS&DESK TOPS, FLASH DISK,DATA PROJECTOR ETC. | E-LEARNING EDUCATORS & BRANCH EDUCATION CONVENORS | MASTER TRAINERS | 5 DAYS |
| 3RD WEEK MARCH | TRINSET | BRIEFING SESSION | LAP TPOS&DESK TOPS, FLASH DISK,DATA PROJECTOR ETC. | SMT’S & BRANCH SECRETARIES | MASTER TRAINERS & ROB’S | 2 DAYS |
| 3RD WEEK MARCH | TRINSET | TRAINING | SAME | E-LEARNING EDUCATORS FROM SITES | MASTER TRAINERS & TRAINEES | 5 DAYS |
| 4TH WEEK MARCH | SITE/BRANCHES | TRAINING | SAME | FET EDUCATORS | E-LEARNING EDUCATORS | CONTINUOUS |
| 4TH WEEK APRIL | SITES | IMPLEMENTATION & MORNITORING | SAME | FET-EDUCATORS | SMT’S & BRANCH EDUCATION CONVENORS | CONTINUOUS |
| 1ST WEEK MAY | SITES | IMPACT ASSESSMENT | ASSESSMENT TOOL | FET –EDUCATORS | MASTER TRAINERS & EDUCATION CONVENORS | CONTINUOUS |